## Sheet1
Defect ID | Module | Test Case ID | Description | Severity | Priority | Status | Reported By | Date Reported | Assigned To | Resolution
DF-001 | Customer Onboarding | TC-001 | CIF not generated after form submission despite valid input | High | P1 | Open | Joseph Olowe | 2025-06-25 | Dev Team
DF-002 | Loan Origination | TC-002 | Loan reference ID not appearing in confirmation screen | Medium | P2 | In Progress | Grace Nwachukwu | 2025-06-26 | Dev Team
DF-003 | Account Maintenance | TC-003 | Phone number update not reflecting in UI after saving | Low | P3 | Open | Bode Ajayi | 2025-06-26 | Frontend Team